## Cover Sheet
Phius Quality Control Workbook for Multifamily Projects - v2.3.3 (May 2023)
Project Name |  | Project Permit Date | Phius Project Number | Total # Buildings | Total # Dwelling Units | Total # Stories per Building | Do dwelling units occupy >80% of occupiable sqft of buildings? | Do dwelling units have individual heating, cooling, and water heating systems?
[7 empty] | [Select] | [Select]
Street Address |  |  | City |  | State/Province |  | Zip Code | Country
[5 empty] | [Select] |  |  | [Select]
PROJECT TEAM |  | Company Name |  | Contact Name |  | CO-REQUISITE PROGRAM ELIGIBILITY
Phius Certified Verifier | [5 empty] | Select the applicable eligibility based on the Phius Certification Guidebook Appendix G-1.1 Program Eligibility Criteria
Phius Certified Consultant (CPHC)
Architect | [5 empty] | ENERGY STAR Multifamily New Construction (MFNC) |  | [Select]
General Contractor / Builder
HVAC Contractor
Functional Testing Agent | [5 empty] | EPA Indoor airPLUS |  | [Select]
Ducted heating/cooling systems in dwelling units? |  |  |  | [Select]
HVAC Contractor must be H-QUITO / ESTAR Credentialed? |  |  |  | Pending Input |  | DOE ZERO ENERGY READY HOME (ZERH) |  | [Select]
Functional Testing Agent is quailfied per |  |  |  | [Select]
Welcome to the Phius Quality Assurance Workbook for Multifamily Projects!
Certification Criteria The Phius Certification process for multifamily projects includes energy modeling and design consulting performed by a Phius Certified Consultant (CPHC) to demonstrate compliance with Phius program energy performance metrics, as well as on-site verification of all critical project energy features by a Phius Certified Verifier or Rater. For full program requirements, please see Phius Certification Guidebook (v3.1)
Using This Workbook The goal of this workbook is to create a single, organized data collection form that shall be used by Phius Certified Raters and Phius Certified Verifiers to document required on-site verification measures that are required for Phius Certification for multifamily projects. As such, the workbook incorporates the various program requirements of the Phius certification for multifamily buildings process, including best practices for building envelope design/installation, HVAC design/installation, domestic hot water distribution, moisture durability management, and indoor air quality. Information regarding testing protocols, exceptions to requirements and links to outside information are included throughout the document using the red "comments" flags that are embedded at the top right of various cells in the workbook. This workbook shall be used for all multifamily projects, regardless of size. Attached housing is typically certified through Phius as a single project. For multifamily projects that meet the qualification criteria for EPA Energy Star, the project shall also follow the ESTAR MFNC, EPA IAP and ZERH certification protocol for all dwelling units within the project. Certification of individual dwelling units may require checklists be documented for each individual dwelling unit. The Phius Certified Rater or Verifier shall discuss checklist documentation requirements with their QA Provider to determine what the Provider will require.
There are eight worksheets to complete (see the tabs below).
Responsible parties for completing each tab are listed here.
Building Envelope |  |  | Phius Certified Verifier or Rater
Compartmentalization |  |  | Phius Certified Verifier or Rater
Ventilation |  |  | Phius Certified Verifier or Rater
Heat + Cool |  |  | HVAC Designer/Contractor, Phius Certified Verifier or Rater
Domestic Hot Water |  |  | Phius Certified Verifier or Rater
Lighting, Cooking & Electric Loads |  |  | Phius Certified Verifier or Rater
Electric Vehicle Readiness |  |  | Phius Certified Verifier or Rater
Co-Requisite Programs |  |  | Phius Certified Verifier or Rater
Data entry cells (for the Rater or Verifier, Builder, HVAC contractor, or designer are in light blue. Checkbox cells are in white. Calculation cells are in light gray. Do not change the calculation cells!
Phius Certified Verifiers/Raters are welcome to add their own custom sheets to this workbook for instance, to track project notes.
Questions regarding particular checklist items should be directed first to the Phius Verifier or Rater for the project. - Conact the Phius QA/QC Manager at QA@phius.org for questions on the nuances between certifying an entire building under Phius and certifying individual dwelling units within such buildings under ESTAR/ZERH - Contact certification@phius.org for any and all question regarding the certification process for any project.
Workbook updates:
v1.1 - 2/3/17: Updated kitchen exhaust criteria, spelling updates, added solar/renewable ready criteria.
v2.2 - 2/9/19: Updated for PHIUS+ 2018 Standards, Footnote (2)
v2.3 - 2/20/2020: Updated for EPA Energy Star MFNCP
v2.3 - 7-20-2021: Updates for current RESNET Standards and Energy Star MFNCP
v2.3 - 01-06-2022: Various wording and formatting updates
v2.3 - 09-26-2022: Alignment with Phius 2021. Electrification Readiness, Electric Vehcile Readiness Requirements, Re-organized Building Envelope, Heat+Cool, and Ventilation tabs, DHW temperature rise sampling table added.
v2.3.1 - 01-26-2023: Updates to the 'Ventilation'. Corrections made to 'pass' and 'fail' criteria for ventilation rates on individual rooms.
v2.3.2 - 04-17-2023: Updates to the 'Ventilation'. Corrections made to 'pass' and 'fail' criteria for Bedroom Pressure Difference inputs. Also updated 'pass' and 'fail' criteria for Heat + Cool for ducted systems.
v2.3.3 - 05-16-2023: Updated formulas for the preliminary blower door test on the 'Building Envelope' tab.
Footnotes (1) Projects located outside of the United States, or in California or Alaska, will not be required to meet ESTAR, IAP and ZERH certifications, regardless of their configuration.
(2) Multi-Family Projects with a Building Permit date after July 1st, 2021 will be required to meet the EPA Energy Star Multi-Family New Construction Program Certification Criteria. For projects permitted prior to that date, Energy Star Certification can be attained by using either Energy Star Homes OR the Energy Star MFNCP subject to implementation dates required by the EPA for their programs.
Note on C17: Note: A contractor credentialed by an H-QUITO is only permitted to complete Sections 1-5 of the ES MFNC Functional Testing checklist.

## Data (hidden)
[Select] | [Select] | [Select] | [Select] | [Select Room Type] | [Select] | [Select]
Yes | AL Alabama | United States | Certification Required | Bedroom | MERV 3+ | Credentialed per listing on www.energystar.gov/ftas
No | AK Alaska | Canada | Compliance Required, Certification not Required | Other | Washable Mesh | Licensed Professional Mechanical Engineer
Heating/Cooling Only | AS American Samoa | Mexico | No Requirements |  |  | Representative of the Original Equipment Manfacturer (OEM)
Water Heating Only | AZ Arizona | Afghanistan
| AR Arkansas | Albania
| CA California | Andorra
| CO Colorado | Angola
| CT Connecticut | Argentina
| DE Deleware | Armenia
| FM Fed. States of Micronesia | Australia
| FL Florida | Azerbaijan
| GA Georgia | Bahamas, The
| GU Guam | Bahrain
| HI Hawaii | Bangladesh
| ID Idaho | Barbados
| IL Illinois | Belgium
| IN Indiana | Benin
| IA Iowa | Bhutan
| KS Kansas | Bolivia
| KY Kentucky | Bosnia & Herzegovina
| LA Louisiana | Botswana
| ME Maine | Brunei
| MD Maryland | Bulgaria
| MH Marshall Islands | Burkina Faso
| MA Massachusetts | Burma
| MI Michigan | Burundi
| MN Minnesota | Cambodia
| MS Mississippi | Cameroon
| MO Missouri | Cape Verde
| MT Montanta | Cayman Islands
| NE Nebraska | Central African Rep.
| NV Nevada | Chad
| NH New Hampshire | Chile
| NJ New Jersey | China
| NM New Mexico | Colombia
| NY New York | Comoros
| NC North Carolina | Congo, Dem. Rep.
| ND North Dakota | Congo, Repub. of the
| MP Northern Mariana Is. | Cook Islands
| OH Ohio | Costa Rica
| OK Oklahoma | Cote d'Ivoire
| OR Oregon | Croatia
| PW Palau | Cuba
| PA Pennsylvania | Cyprus
| PR Puerto Rico | Czech Republic
| RI Rhode Island | Denmark
| SC South Carolina | Djibouti
| SD South Dakota | Dominica
| TN Tennessee | Dominican Republic
| TX Texas | East Timor
| UT Utah | Ecuador
| VT Vermont | Egypt
| VA Virginia | El Salvador
| VI Virgin Islands | Equatorial Guinea
| WA Washington | Eritrea
| WV West Virginia | Estonia
| WI Wisconsin | Ethiopia
| WY Wyoming | Faroe Islands
| AB Alberta | Fiji
| BC British Columbia | Finland
| MB Manitoba | France
| NB New Brunswick | French Guiana
| NF Newfoundland | French Polynesia
| NT Northwest Territories | Gabon
| NS Nova Scotia | Gambia, The
| ON Ontario | Gaza Strip
| PE Prince Edward Island | Georgia
| QC Quebec | Germany
| SK Saskatchewan | Ghana
| YT Yukon | Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
Hong Kong
Hungary
Iceland
India
Indonesia
Iran
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Korea, North
Korea, South
Kuwait
Kyrgyzstan
Laos
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Macau
Macedonia
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Micronesia, Fed. St.
Moldova
Monaco
Mongolia
Montserrat
Morocco
Mozambique
Namibia
Nauru
Nepal
Netherlands
Netherlands Antilles
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
N. Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Puerto Rico
Qatar
Reunion
Romania
Russia
Rwanda
Saint Helena
Saint Kitts & Nevis
Saint Lucia
St Pierre & Miquelon
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome & Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syria
Taiwan
Tajikistan
Tanzania
Thailand
Togo
Tonga
Trinidad & Tobago
Tunisia
Turkey
Turkmenistan
Turks & Caicos Is
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom
Uzbekistan
Vanuatu
Venezuela
Vietnam
Virgin Islands
Wallis and Futuna
West Bank
Western Sahara
Yemen
Zambia
Zimbabwe

## Building Envelope
Building Envelope Phius On-site Quality Control
The Phius Certifier Verifier or Rater is responsible for verifying all items on this worksheet For projects with multiple buildings, please create a duplicate worksheet for each building in the project.
1 | Site Photos and Verification |  |  | Verifier Confirmed | N/A
1.1 | Take as many exterior photos as needed to appropriately depict all building elevations and significant architectural features of building for documentation folder
1.2 | Take pictures of surrounding site on all sides of building
1.3 | Take representative pictures of all unique insulated assemblies and window/door installations
1.4 | Perform thorough IR scan of entire building from interior and exterior, including all dwelling units and common spaces, and document representative photos
1.5 | If installed, describe operable shading. Include photo/s in documentation folder
Rater Notes:
2 | Verification of Architectural Features |  |  | Verifier Confirmed | N/A
2.1 | Drawings Check - describe any significant variations in construction from the construction drawings and specifications (insulation, window sizes, window performance, fixed shading etc.)
Rater Notes:
2.2 | Insulation R-value: All insulation R-values match those listed on architectural plans. If not, please describe in notes section below.
Rater Notes:
2.3 | All insulated assemblies have achieved a RESNET Grade I cavity insulation level, or alternatively GII with continuous insulation.
2.4 | Framing inspection: Framing matches architectural plans. If not, please describe in notes section below.
Rater Notes:
3 | Building Airtightness Testing
3.1 | Blower Door Test Threshold Calculator | Building is 5+ stories in height, of non-combustible construction? |  | [Select]
Building Envelope Area (ft2)
|  | Project Threshold (CFM50/ft2) |  | Pending Input
Project Threshold (CFM50)
3.2 | Optional whole building preliminary blower door test (manual or automated test) | Preliminary Test | (CFM50/ft2) | CFM50
Depressurization Test Result
Pressurization Test Result
Average Test Result
3.3 | Final whole building blower door test Multi-point test in accordance with ANSI/RESNET/ICC 380-2019 | Final Test | (CFM50/ft2) | CFM50
Depressurization Test Result
Pressurization Test Result
Average Test Result
Criteria Passed?
Note on D10: Follow RESNET Infrared inspection guidelines for minimum delta-T. Images should include walls, insulated ceilings, slabs, windows. Use picture in picture if camera has the capability. Enter "n/a" if conditions do not allow the minimum delta-T
Note on D18: Please see RESNET Standards Appendix A for information on insulation Grading

## Compartmentalization
Unit Compartmentalization Phius On-site Quality Control
Dwelling Unit Compartmentalization Test: Compartmentalization testing shall be performed to test air tightness of individual dwelling units. The test threshold shall be 0.3 CFM50 / sq ft of unit Shell Area, otherwise known as Envelope Leakage Ratio (ELR). Testing may be performed using RESNET Chapter 6 Sampling protocols, and may be performed in either depressurization or pressurization mode. Sampling is typically appropriate for projects of at least 30 or more dwelling units. Please discuss with your RESNET QA Provider and/or Phius to ensure they will support Sampling being applied to the project. Please document compartmentalization results below.
Testing protocol
Testing shall be performed following RESNET/ANSI Standard 380-2019 and RESNET Standards for Multifamily Energy Ratings.
https://www.resnet.us/about/standards/resnet-ansi/
Sampling Documentation
Total project dwelling units |  |  | # Units Initial Sampling Qualifying set |  |  |  | # of add'l Sampled Units
Initial Sampling Qualifying Set
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | Unit 7
Unit #
Shell Area SF
CFM@50 Pa
ELR
| Did any units fail (and had to be corrected) during Initial Sampling Qualifying Set? | [6 empty] | Yes
If yes, how many additional units were tested in Qualifying Set?
[5 empty] | Unit X | Unit Y | Unit Z
Unit #
Shell Area SF
CFM@50 Pa
ELR
Based on number of Sampled Units listed above, create a summary document of compartmentalization testing for each. Sample Sets and Sampling Rates are to follow RESNET MINHERS Chapter 6 Technical Requirements. Please refer to that Standard for more specific information. For purposes of this Workbook, an intial set of 7 units will be tested without failure and the results provided above in "Intitial Sampling Qualifying Set". If no failures, then proceed with testing 1/7th of the remaining units rounding up for the unit total and provide the results below in "Sample Set 1, & Sample Set 2". If failures occured and addtional units were tested, report those results above in the boxes marked "Unit X, Unit Y" etc. Please copy and paste the example Sample Set documentation sequentially below. Add or copy if additonal space is needed.
Sample Set 1
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | Unit 7
Unit #
Unit SFBE
CFM@50 Pa
ELR
Sample Set 2
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | Unit 7
Unit #
Unit SFBE
CFM@50 Pa
ELR

## Ventilation
Ventilation Phius On-site Quality Control
The Rater/Verifier is responsible for verifying all dwelling unit ventilation items on this worksheet. Ventilation air volume measurements may be verified by a third-party air balancing contractor so long as the Rater/MF Verifier verifies a minimum of 10%, or 10, units, whichever is lower (but no less than 3). The items on this worksheet that pertain to dwelling unit ventilation must be verified with an individual worksheet for each individual dwelling unit. Alternatively, the Rater has the option to use the RESNET Sampling protocol to verify the dwelling unit ventilation criteria. For projects with common spaces, Rater shall be responsible for collecting air balance documentation for all common space ventilation systems, documenting the design ventilation rate and the final verified air balance rate.
1 | Dwelling Unit Ventilation System Installation | [13 empty] | Verifier Confirmed | N/A
| 1.1 | [9 empty] | 1.2 |  | 1.6 | 1.8
| System Type |  |  | Manufacturer |  | Model # |  |  | Quantity |  | Photo(s) Provided |  | MERV | Duct R-Value
1.2 | Ventilation manufacturer & model number(s) on installed equipment matches Nation HVAC Design Report or Substitutions have written approval from desiginer
| 1.2.1 | Rater/Verifier has confirmed and verified all items in Section 7,8 & 9 On the National Rater Field Checklist for ES MFNC have been completed and are satisfactory
1.3 | All ventilation air inlets located ≥ 10' ("stretched-string distance") from known contamination sources.
1.4 | Ventilation air inlets are not obstructed by snow, plantings, outdoor equipment, or other material at the time of inspection and comply with either:
| 1.4.1 | Project in Climate Zones 1-3: ≥ 2' above grade and/or roof deck
| 1.4.2 | Project in Climate Zones 4-8: ≥ 4' above grade and/or roof deck
1.5 | Ventilation air comes directly from outdoors, not from adjacent dwelling units, common spaces, garages, crawlspaces or attics.
1.6 | Outside air passes through a minimum MERV 8 filter prior to distribution.
1.7 | Outside air filter is located to facilitate regular service by the occupant and/or building superintendent.
1.8 | Air-sealed, class 1 vapor retarder shall be installed over all air-permeable insulation (such as fiberglass duct wrap) on ventilation ducts connected to outside. Vapor retarder is continous and sealed to building air barrier and ventialtion unit with no gaps, breaks or holes.
1.9 | Provision made to supply fresh air to all bedrooms in dwelling units and comply with either 1.9.1 or 1.9.2.
| 1.9.1 | Dedicated fresh air supply ventilation ductwork installed to all bedrooms. | [12 empty] | [Select]
| 1.9.2 | Fresh air supply ventilation ductwork integrated with heating/cooling ductwork. | [12 empty] | Yes
| 1.9.2.1 |  | ERV/HRV remains in balance under all fan speeds of the heating/cooling air handler. | [10 empty] | Required
| 1.9.2.2 |  | Air handler fan designed to run continuously by default. | [10 empty] | Required
| 1.9.3 | Bedrooms are pressure balanced to achieve a Verifier measured pressure difference of no more than 1 Pa with respect to the main body of the apartment when all bedroom doors are closed and just the ventilation system is operating at design speed. (Fill out Section 2.3) | [12 empty] | -
1.1 | Rater/Verifier - measured bathroom exhaust rates meets one of the following:
| 1.10.1 | ≥20cfm continuous. | [12 empty] | [Select]
| 1.10.2 | ≥50 cfm intermittent. | [12 empty] | [Select]
1.11 | Rater/Verifier - measured kitchen exhaust rates meets one of the following:
| 1.11.1 | ≥25cfm continuous. | [12 empty] | [Select]
| 1.11.2 | ≥100cfm intermittent for direct exhaust range hood(s). | [9 empty] | (Enter Airflow) [cfm] |  |  | [Select]
| 1.11.3 | ≥5ACH based on kitchen volume. | [12 empty] | [Select]
1.12 | ERV/HRV exhaust register in kitchen: | [13 empty] | [Select]
| 1.12.1 | Exhaust register installed ≥ 6' from cooktop. ("stretched-string distance") | [12 empty] | [Select]
| Confirm which type of filter for trapping grease installed (MERV 3+ or Washable Mesh) | [13 empty] | [Select]
| Recirculating hood over range installed. | [13 empty] | [Select]
1.13 | Check all types of clothes dryer(s) installed:
| 1.13.1 | Condensing Dryer
| 1.13.2 | Heat Pump Dryer
| 1.13.3 | Exhaust Air Dryer with exhaut ducted to the outside
2 | Ventilation System Airflow Testing Verification
Where ventilation system has independent ductwork for supply and/or exhaust, branch airflow testing is to be performed by Phius Certified Verifier or Phius Certified Rater.
Status
2.1 | Total airflow at unit (HRV/ERV) at maximum speed setting. | [6 empty] | E/HRV # | Design Airflow (cfm) |  | Verified Airflow (cfm) |  | Verified ≥ Design |  | Within 10% of each other
[9 empty] | Supply | Exhaust | Supply | Exhaust | Supply | Exhaust
[13 empty] | - | - | -
[13 empty] | - | - | -
[13 empty] | - | - | - |  | `
2.2 | Ventilation system(s) at max has capacity to exchange 0.30 ACH | [9 empty] | Net Volume (ft3) |  | Total Airflow (cfm) |  | ≥0.3 ACH
[13 empty] | Supply | Exhuast
-
2.3 | Typical 24/7 Supply Design Airflow Rates
| The ventilation rates of the individual diffusers should be measured at the typical 24/7 ventilation rate. For additional E/HRVs, duplicate this tab. | [9 empty] | Airflow (cfm) |  | Room Pressure Difference [Pa] | Status
| E/HRV # |  | Dwelling Unit # |  | Supply Room Name |  | Room Type |  |  |  | Design (cfm) | Verified (cfm) |  | ≥Design | Within +5cfm or +20% | <1 Pa Pressure Difference
[5 empty] | enter supply branch name here |  | Bedroom | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
| E/HRV # |  | Dwelling Unit # |  | Supply Room Name |  | Room Type |  |  |  | Design (cfm) | Verified (cfm) |  | ≥Design | Within +5cfm or +20% | <1 Pa Pressure Difference
| 2.3.2 |  |  |  | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
Sum of supply branches (for reference only)
| E/HRV # |  | Dwelling Unit # |  | Supply Room Name |  | Room Type |  |  |  | Design (cfm) | Verified (cfm) |  | ≥Design | Within +5cfm or +20% | <1 Pa Pressure Difference
| 2.3.3 |  |  |  | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter supply branch name here |  | -Select Room- | [6 empty] | - | - | -
Sum of supply branches (for reference only)
2.4 | Typical 24/7 Exhaust Design Airflow Rates
| The ventilation rates of the individual diffusers should be measured at the typical 24/7 ventilation rate. For additional E/HRVs, duplicate this tab. | [9 empty] | Airflow |  |  | Status
| E/HRV # |  | Dwelling Unit # |  | Exhaust Room Name |  | Room Type |  |  |  | Design (cfm) | Verified (cfm) |  | ≥Design | Within +5cfm or +20% | ≥Minimum
| 2.4.1 |  |  |  | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
Sum of exhaust branches (for reference only)
| E/HRV # |  | Dwelling Unit # |  | Exhaust Room Name |  | Room Type |  |  |  | Design (cfm) | Verified (cfm) |  | ≥Design | Within +5cfm or +20% | ≥Minimum
| 2.4.2 |  |  |  | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
Sum of exhaust branches (for reference only)
| E/HRV # |  | Dwelling Unit # |  | Exhaust Room Name |  | Room Type |  |  |  | Design (cfm) | Verified (cfm) |  | ≥Design | Within +5cfm or +20% | ≥Minimum
| 2.4.3 |  |  |  | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
[5 empty] | enter exhaust branch name here |  | -Select Room- | [6 empty] | - | - | -
Sum of exhaust branches (for reference only)
2.5 | Total airflow at unit (HRV/ERV) for typical operation. | [6 empty] | E/HRV # | Design Airflow (cfm) |  | Verified Airflow (cfm) |  | ≥Design |  | Within 10% of each other
[9 empty] | Supply | Exhaust | Supply | Exhaust | Supply | Exhaust
[8 empty] | 1 |  |  |  |  | - | - | -
[8 empty] | 2 |  |  |  |  | - | - | -
[8 empty] | 3 |  |  |  |  | - | - | -
2.6 | Measure power input (Watts) at typical 24/7 airflow setting | [6 empty] | E/HRV # |  |  | Measured Fan Power Input (W) |  | Fan Power (W/cfm)
[8 empty] | 1 |  |  |  |  | -
[8 empty] | 2 |  |  |  |  | -
[8 empty] | 3 |  |  |  |  | -
3 | Ventilation - Auxiliary Systems | [13 empty] | Verifier Confirmed | N/A
3.1 | If installed, enter type of ERV/HRV defrost - electric, hot water loop from DHW tank, ground loop
3.2 | Project team has demonstrated the defrost control logic is set up properly
3.3 | Is there a ground loop ("brine loop") or earth tube installed?
| 3.3.1 | Enter loop length and approximate depth
| 3.3.2 | Measure loop pump power
| 3.3.3 | Project team has demonstrated the ground loop / earth tube control logic is set up properly
4 | Common Space Ventilation System Installation | [13 empty] | Verifier Confirmed | N/A
4.1 | Rater performed common space ventilation testing on all common space ventilation systems, or alternatively has collected air balancing documentation from HVAC Contractor or certified air balancing professional which documents the design and verified rate, runtime, and wattage.
4.2 | Rater documented common space ventilation system information (List all installed ventilation systems)
| 4.2.1 |  |  | 4.2.2 |  | 4.2.3 |  |  | 4.2.4 |  | 4.2.5 |  | 4.2.6 | 4.2.7
| System Type |  |  | Manufacturer |  | Model # |  |  | Quantity |  | Photo(s) Provided |  | MERV | Duct R-Value
| 4.2.8 |  |  |  |  | 4.2.9 |  |  |  | 4.2.10 |  |  |  | 4.2.11
| Common Space Zone |  |  |  |  | System Type |  |  |  | Manufacturer |  |  |  | Model #
(copy above line if more required to be documented)

## Sheet1 (hidden)
Dropdown Options
-Select Room- | -Select Room-
Bedroom | Bathroom
Living Room | 1/2 Bath
Dining Room | Kitchen
Corridor | Laundry
Multipurpose | Trash
Other | Mechanical
Other
-Select Type- | -Select Type-
ERV | Dwelling unit
HRV | Shared
Exhaust Only
Supply Only
Air Cycler

## Heat + Cool
Heating + Cooling Phius On-site Quality Control
Complete form for each piece of heating/cooling equipment with air distribution. Additional heating/cooling checks listed for items 4 and beyond. For example, if each apartment has its own heat pump, complete one form for each apartment. Copy and past additional forms/sheets into this workbook as needed. Ducted heating/cooling air volume measurements may be verified by a third-party air balancing contractor so long as the Rater/MF Verifier verifies a minimum of 10% of or 10, units, whichever is lower (but no less than 3). The items on this worksheet that pertain to dwelling unit heating/cooling systems must be verified with an individual worksheet for each individual dwelling unit. Alternatively, the Rater has the option to use the RESNET Sampling protocol to verify the dwelling unit heating/cooling air volume measurement criteria. For projects with common spaces, Rater shall be responsible for collecting air balance documentation for all common space ventilation systems, documenting the design ventilation rate and the final verified air balance rate.
1 | Heating/Cooling Equipment | [7 empty] | Verifier Confirmed | HVAC Contractor Verified | N/A
1.1 | System type (split heat pump, water source heat pump, fan coil, furnace, hydronic, etc.)
1.2 | "Central" or "Per Apartment" distribution, ducted or ductless?
1.3 | Manufacturer + model #
1.4 | AHRI certificate and/or manufacturer's detailed specs for heating/cooling equipment are included in documentation folder
1.5 | Photos of equipment (including model numbers) are included in documentation folder
1.6 | If a combustion equipment for space heating, the building has provided a designated exterior location(s) in accordance with the following*
*Exception: Where an electrical circuit in compliance with IRC Section E3702.11 exists for space cooling equipment.
| A | Natural drainage for condensate from cooling equipment operation or a condensate drain located within 3 feet
| B | A dedicated branch circuit in compliance with IRC Section E3702.11 based on heat pump space heating equipment sized in accordance with R403.7 and terminating within 3 feet of the location with no obstructions. Both ends of the branch circuit shall be labeled “For Future Heat Pump Space Heater.”
2 | Heating/Cooling Distribution - Ducted Systems Only | [7 empty] | Verifier Confirmed | HVAC Contractor Verified | N/A
2.1 | Duct layout drawing, total system design airflow and branch design airflows are included in documentation folder
2.2 | Rater review of duct installation:
| A | Duct installation reasonably matches design layout
| B | Building cavities not used as supply or return ducts
2.3 | All return air passes through a minimum MERV 8 filter
2.4 | Filter access panel includes a gasket or comparable sealing mechanism
2.5 | Rater has measured and documented the branch airflow balancing to be within specifications (the greater of +/- 20% or 25cfm of design value)
2.6 | Bedrooms are pressure balanced to achieve a Rater-measured pressure difference of no more than 3Pa with respect to the main body of the house/apartment when all bedroom doors are closed, all heating/cooling air handlers are operating at full speed and ventilation system is operating at design speed
2.7 | Total system and branch airflow testing - to be performed by Phius Certified Verifier or Rater. Phius Certifier Verifier/Rater conducted balancing is optional. |  | Design (cfm) | Verified (cfm) | % +/- Design | cfm +/- Design | OK? | Room pressure difference [Pa] |  | OK?
| TOTAL System Airflow | [5 empty] | YES
| Bedroom |  |  |  |  | N/A | NO |  |  | NO
| [Select Room Type] |  |  |  |  | N/A | NO |  |  | NO
| [Select Room Type] |  |  |  |  | N/A | NO |  |  | NO
| [Select Room Type] |  |  |  |  | N/A | NO |  |  | NO
| [Select Room Type] |  |  |  |  | N/A | NO |  |  | NO
| [Select Room Type] |  |  |  |  | N/A | NO |  |  | NO
| [Select Room Type] |  |  |  |  | N/A | NO |  |  | NO
3 | Refrigerant Testing, Controls + Electrical Measurements | [7 empty] | Verifier Confirmed | HVAC Contractor Verified | N/A
3.1 | Fan - air flow is produced when thermostat is set to "fan on"
3.2 | Heated air flow is produced when thermostat is set to "heat"
3.3 | Cooling air flow is produced when thermostat is set to "cool"
4 | Combustion furnaces, boilers and/or water heaters located within the buildings' pressure boundary are sealed combustion, direct-vent appliances
5 | Natural draft fireplaces are not installed
6 | Installed woodstoves have a combustion air inlet connected to the firebox
7 | Corrosion-resistant drain pan, properly sloped to drainage system is included with each HVAC component that produces condensate
8 | Heating/Cooling Distribution - Hydronics
8.1 | Pipe layout drawing + schedule showing pipe sizes and insulation is included in documentation folder
8.2 | Rater review of pipe + pump installation:
| 8.2.1 | Pipe installation reasonably matches design layout
| 8.2.2 | Pipe insulation matches design specs
| 8.2.3 | Pump/s Manufacturer + Model #
| 8.2.4 | Is pump single speed or variable?
| 8.2.5 | Design hydronic loop flow rate (GPM)
| 8.2.6 | Measured hydronic loop flow rate (GPM)
| 8.2.7 | Measure pump power input

## Domestic Hot Water
Domestic Hot Water (DHW) Phius On-site Quality Control
1 | Domestic Hot Water (DHW) | [6 empty] | Verifier Confirmed
1.1 | Project team has provided Plumbing drawings with DWH lengths, diameter and insulation specs
1.2 | Hot water pipe install generally matches the design (length, diameter and insulation)? Describe any differences below:
Rater Notes:
1.3 | All hot water systems and associated pumps are verified to be accurate per project specifications
1.4 | DHW is "central system" or "individual apartment" systems?
1.5 | Recirculation system installed? If so, please describe
1.6 | Dwelling Unit Hot Water Distribution Temperature Rise Test Completed
| Exception: On-Demand central systems in multifamily projects have no stored volume limit. The watersense test shall still be run. |  |  |  |  | On-Demand Central System? | [Select]
1.7 | Combustion water heating and water heater capacity is less than or equal to 300,000 Btu/h (88 kW). If yes, the following must be met. | [5 empty] | [Select]
| A | A dedicated 240-volt branch circuit with a minimum capacity of 30 amps shall terminate within 3 feet from the water heater and be accessible to the water heater with no obstructions. Both ends of the branch circuit shall be labeled with the words "For Future Heat Pump Water Heater" and be electrically isolated.
| B | A condensate drain is installed within 3 feet of the water heater. It is no more than 2 inches higher than the base of the installed water heater and allows natural draining without pump assistance.
| C | The water heater is installed in a space with minimum dimensions of 3 feet x 3 feetx 7 feet high.
| D | The water heater is installed in a space with a minimum volume of 700 cubic feet or the equivalent of one 16-inch x 24-inch grill to a heated space and one 8-inch duct of no more than 10 feet in length for cool exhaust air.
1.8 | Combustion water heating and water heater capacity is greater than or equal to 300,000 Btu/h (88 kW). If yes, the following must be met. | [5 empty] | [Select]
Is provided with a branch circuit sized for an electric appliance, equipment or end use with an equivalent capacity that terminates within 6 feet of the appliance or equipment
Watersense Hot Water Distribution Rise: Sampling Documentation
Multifamily buildings ≤5 stories with unitary/per-unit water heaters shall have domestic water heating systems that meet Path A or Path B below (following requirements of Sections 15 & 16 of DOE ZERH National Program Requirements Rev07 dated May 1, 2019). Path A: Dwelling unit hot water distribution temperature rise test: Each dwelling unit shall have its highest volumetric plumbing run tested for temperature rise. A maximum of 0.6 Gal shall be emitted from the highest volumetric plumbing run before the hot water temperature rises 10 deg F. Path B: Equipment Efficiency and Compliant Taps: Comply with criteria for minimum water heater efficiency levels and the use of WaterSense showerheads and bathroom sink faucets. A maximum of 1.4 Gal shall be emitted from the highest volumetric plumbing run before the hot water temperature rises 10 deg F. Phius strongly discourages, but shall not prevent the use of continuous or time-based hot water circulation systems in multifamily buildings of 6 or more stories and in non-residential projects. Advisories: • On-demand central recirculation systems in multifamily buildings do not currently have a stored volume limit. DOE encourages partners to design central hot water distribution systems in multifamily buildings to limit the stored volume to 1.0 gallons between the recirculation loop and the furthest fixture. • Piping for central system recirculation loops in multifamily buildings should be insulated per the local code requirements. DOE encourages the use of R-4 pipe insulation on recirculation loop piping. • DOE encourages that the recirculation pump for central systems be set to operate at a temperature which is at least 5°F less than the water heater set point temperature.
Total project dwelling units |  |  | # Units Initial Sampling qualifying set |  |  | 7 | # Sampling sets
Initial Sampling Qualifying Set
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | Unit 7
Unit #
Gallons emitted
Passes? | Pending | Pending | Pending | Pending | Pending | Pending | Pending
| Did any units fail (and had to be corrected) during Initial Sampling Qualifying Set? | [6 empty] | [Select]
If yes, how many additional units were tested in Qualifying Set?
[5 empty] | Unit X | Unit Y | Unit Z
Unit #
Gallons emitted
|  |  |  | Passes? | Pending | Pending | Pending
Based on number of Sampled Units listed above, create a summary document of hot water temp rise testing for each. Sample Sets and Sampling Rates are to follow RESNET MINHERS Chapter 6 Technical Requirements. Please refer to that Standard for more specific information. For purposes of this Workbook, an intial set of 7 units will be tested without failure and the results provided above in "Intitial Sampling Qualifying Set". If no failures, then proceed with testing 1/7th of the remaining units rounding up for the unit total and provide the results below in "Sample Set 1, & Sample Set 2". If failures occured and addtional units were tested, report those results above in the boxes marked "Unit X, Unit Y" etc. For MF Projects where sampling is not practical, Phius requires verification of a minimum of 10% of the dweeling units, but no less than three (3). Please copy and paste the example Sample Set documentation sequentially below. Add or copy if additonal space is needed.
Sample Set 1
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | Unit 7
Unit #
Gallons emitted
Passes? | Pending | Pending | Pending | Pending | Pending | Pending | Pending
Sample Set 2
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | Unit 7
Unit #
Gallons emitted
Passes? | Pending | Pending | Pending | Pending | Pending | Pending | Pending

## Lighting, Cooking & Elec Loads
Appliances, Cooking, Lighting & Electric Loads Phius On-site Quality Control
1 | Appliances | [6 empty] | Verifier Confirmed
1.1 | Refrigerators | Manufacturer | Model # | Quantity | Energy Use (kWh/yr) | ENERGY STAR? | Capacity (ft3)
1.2 | Type 1
1.3 | Type 2
1.4 | Type 3
1.5 | Weighted Average |  |  |  | - | - | -
2 | Dishwashers | Manufacturer | Model # | Quantity | Energy Use (kWh/yr) | ENERGY STAR? | Capacity (ft3)
2.1 | Type 1
2.2 | Type 2
2.3 | Type 3
2.4 | Weighted Average |  |  |  | - | - | -
3 | Clothes Washers | Manufacturer | Model # | Quantity | Energy Use (kWh/yr) | Modified Energy Factor (MEF) | Capacity (ft3)
3.1 | Type 1
3.2 | Type 2
3.3 | Type 3
3.4 | Weighted Average |  |  |  | - | - | -
4 | Clothes Dryers | Manufacturer | Model # | Quantity | Combined Energy Factor (CEF) | Moisture Sensing? | Fuel Type
4.1 | Type 1
4.2 | Type 2
4.3 | Type 3
4.4 | Weighted Average |  |  |  | -
4.5 | Combustion Clothes Drying is installed | [6 empty] | [Select]
A dedicated 240-volt branch circuit with a minimum capacity of 30 amps terminates within 6 feet of natural gas clothes dryers and is accessible with no obstructions. Both ends of the branch circuit shall be labeled with the words “For Future Electric Clothes Drying” and be electrically isolated.
5 | Cooking | [6 empty] | Verifier Confirmed
5.1 | Combustion cooking is installed | [6 empty] | [Select]
5.2 | A dedicated 240-Volt, 40A branch circuit terminates within 6 feet of natural gas ranges, cooktops and ovens and is accessible with no obstructions. Both ends of the branch circuit shall be labeled with the words “For Future Electric Range'' and be electrically isolated.
6 | Lighting | [6 empty] | Verifier Confirmed
6.1 | Project team has provided Rater/Verifier with detailed lighting plan
6.2 | Installed lighting matches lighting plan - describe variations, if applicable
6.3 | Project meets DOE ZERH requirements for dwelling unit lighting, and the common space lighting requirements of ENERGY STAR MFHR
7 | Major Service / Electric Loads | [6 empty] | Verifier Confirmed
7.1 | Project team has provided Verifier/Rater with detailed service mechanical / electrical equipment plan/schedule?
7.2 | Installed air handlers, pumps, motors, etc match the project plans/schedule?
7.3 | Describe variations:
7.4 | Rater/Verifier provided electrical commissioning reports from third-party balancing/commissioning agent with electrical measurements?
8 | Renewable Energy Systems | [6 empty] | Verifier Confirmed
8.1 | Project team has installed a renewable energy system (take photos of system and any inverters)
8.2 | If no renewable energy system installed, project has completed provisions of DOE Zero Energy Ready Homes PV Ready Checklist

## Electric Vehicle Readiness
Electric Vehicle Readiness Phius On-site Quality Control
1 | Electric Vehicle Charging Infrastructure |  |  |  | Verifier Confirmed
Infrastructure for the current and future charging of electric vehicles (EVs) is required for all residential buildings where parking spaces are required. The number of EV Ready and EV Capable Spaces required depends on the building’s parking requirement. EV ready spaces are permitted to be counted toward meeting minimum parking requirements.
1.1 | EV-Ready and EV-Capabale spaces are provided per the table and calculation below.
|  | Total # of Parking Spaces | Minimum Number of EV Ready Spaces | Minimum Number of EV Capable Spaces
|  | 1 | 1 | -
|  | 2-10 | 2 | -
|  | 11-15 | 2 | 3
|  | 16-20 | 2 | 4
|  | 21-25 | 2 | 5
|  | 26+ | 2 | 20% of Total
| Input Project Data >> | Total # of Parking Spaces | Minimum Number of EV Ready Spaces | Minimum Number of EV Capable Spaces
|  |  | Input Missing | Input Missing
2 | EV Ready Spaces
2.1 | Minimum number of EV Ready Spaces required are present. |  |  | Input Missing Spaces
2.2 | The branch circuit has wiring capable of supporting a 40-amp, 208/240-volt circuit*
*Exception: For retrofit projects with an existing garage, dual 40 amp, 208/240-volt circuits are allowed rather than single 40 amp, 208/240-volt circuits per EV Ready space.
2.3 | The branch circuit terminates at a junction box or receptacle located within 3 feet of the parking space.
2.4 | The electrical panel directory has designated the branch circuit as “For electric vehicle charging” and the junction box or receptacle shall be labeled “For electric vehicle charging”.
3 | EV Capable Spaces
3.1 | Minimum number of EV Capable Spaces required are present |  |  | Input Missing Spaces
3.2 | The raceway location is permanately and visible marked as 'EV Capable'
3.2 | The conduit is continuous between a junction box or receptacle located within 3 feet of the parking space and an electrical panel serving the area of the parking space with sufficient dedicated physical space for a dual-pole, 40-amp breaker.
3.3 | The conduit is sized and rated to accommodate a 40-amp, 208/240-volt branch circuit and have a minimum nominal trade size of 1 inch.
3.4 | The electrical junction box and the electrical panel directory entry for the dedicated space in the electrical panel have labels stating “For future electric vehicle charging”.

## Co-Requisite Programs
Co-Requisite Program Checklists Phius On-site Quality Control
Checklists - Check the box for all checklists submitted |  |  | Verifier Submitted
1 | ENERGY STAR
1.2 | HVAC Design Report
1.3 | HVAC Rater Design Review Checklist
1.4 | Functional Testing Checklist
1.5 | Rater Field Checklist
1.6 | Water Management System Builder Requirements
2 | EPA Indoor airPLUS
2.1 | EPA Indoor airPLUS Checklist
3 | DOE Zero Energy Ready Homes
3.1 | DOE ZERH PV Ready Checklist